## timeline_table_example
Example Timeline for FCT Research Grant
[5 empty] | Year 1 | [11 empty] | Year 2
Task | Task Denomination | Person*month | Participant responsible for task | Members involved in task | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
A | Start doing stuff | ? | Marge | Marge, Homer | Year 1 1: Task A (6 months)
B | Continue doing stuff | ? | Marge | Marge, Homer, Bart | Year 1 4: Task B (5 months)
C | Analyze stuff | ? | Marge | Marge, Lisa | Year 1 7: Task C (8 months)
D | Conclude stuff | ? | Marge | Homer, Bart, Marge, Lisa | Year 1 12: Task D (7 months)
| Total | ?? |  |  | Year 1 4: M1; Year 1 9: M2; Year 2 14: M3; Year 2 18: M4
[13 empty] | Progress Report | [6 empty] | Final Report
Expected Input Table (for timeline above)
task | member | start_month | total_months | eti_percentage
Task A | Marge | 1 | 6 | 50
Task A | Homer | 1 | 6 | 25
Task B | Marge | 4 | 5 | 50
Task B | Homer | 4 | 5 | 25
Task B | Bart | 4 | 5 | 15
Task C | Marge | 7 | 8 | 50
Task C | Lisa | 7 | 8 | 75
Task D | Homer | 12 | 7 | 25
Task D | Bart | 12 | 7 | 15
Task D | Marge | 12 | 7 | 50
Task D | Lisa | 12 | 7 | 75

## test1_works
task | member | start_month | total_months | eti_percentage
Task 1 | Homer | 1 | 4 | 50
Task 1 | Marge | 1 | 4 | 25
Task 2 | Homer | 3 | 6 | 50
Task 2 | Marge | 3 | 6 | 25
Task 2 | Bart | 3 | 6 | 15
Task 2 | Lisa | 3 | 6 | 75
Task 2 | Maggie | 3 | 6 | 15
Task 3 | Homer | 1 | 8 | 50
Task 3 | Marge | 1 | 8 | 25
Task 3 | Lisa | 1 | 8 | 75
Task 4 | Homer | 8 | 6 | 50
Task 4 | Marge | 8 | 6 | 25
Task 4 | Bart | 8 | 6 | 15
Task 4 | Lisa | 8 | 6 | 75
Task 5 | Homer | 13 | 6 | 50
Task 5 | Marge | 13 | 6 | 25
Task 5 | Bart | 13 | 6 | 15

## test2_works
task | member | start_month | total_months | eti_percentage
Task A | Marge | 1 | 6 | 50
Task A | Homer | 1 | 6 | 25
Task B | Marge | 4 | 5 | 50
Task B | Homer | 4 | 5 | 25
Task B | Bart | 4 | 5 | 15
Task C | Marge | 7 | 8 | 50
Task C | Lisa | 7 | 8 | 75
Task D | Homer | 12 | 7 | 25
Task D | Bart | 12 | 7 | 15
Task D | Marge | 12 | 7 | 50
Task D | Lisa | 12 | 7 | 75

## test3_fails
task_id | member | start_month | total_months | eti_percentage
Task A | Marge | 1 | 4 | 50
Task A | Homer | 1 | 4 | 25
Task B | Marge | 4 | 6 | 50
Task B | Homer | 4 | 6 | 25
Task B | Bart | 4 | 6 | 15
Task C | Marge | 7 | 8 | 50
Task C | Lisa | 7 | 8 | 75
Task D | Homer | 13 | 6 | 25
Task D | Bart | 13 | 6 | 15
Task D | Marge | 13 | 6 | 50
Task D | Lisa | 13 | 6 | 75

## test4_works
task | total_months | start_month | member | eti_percentage
Task A | 4 | 1 | Marge | 50
Task A | 4 | 1 | Homer | 25
Task B | 6 | 4 | Marge | 50
Task B | 6 | 4 | Homer | 25
Task B | 6 | 4 | Bart | 15
Task C | 8 | 7 | Marge | 50
Task C | 8 | 7 | Lisa | 75
Task D | 6 | 13 | Homer | 25
Task D | 6 | 13 | Bart | 15
Task D | 6 | 13 | Marge | 50
Task D | 6 | 13 | Lisa | 75